## Roles
Role | Definition | Responsibilities
Domain expert | Expert in the domains covered by the ontology. The domain expert does not have to have expertise in ontology engineering. | - Provide knowledge and expertise about the domain of the ontology - Provide requirements - Validate the conceptual adequacy and accuracy of the ontology
Ontology engineer | Technical expert on ontology engineering, responsible for designing, modelign and formalizing the ontology. | - Collection and formalization of requirements from input provided by staekholders or domain experts - Define the ontology’s conceptual structure, classes, properties, and axioms - Align the ontology with existing standards and well-established ontologies. - Implement the ontology in formal representation languages (e.g., OWL, RDF, SKOS) - Publish the ontology in the DS infrastructure (vocabulary hub?) - Manage the ontology maintenance
Software developers | Technical expert that integrates the ontology into operational systems, data workflows, or software applications | - Implement the ontology in the Vocabulary Hub? In the conectors? adapters? - Implement functionalities that consume or expose ontology-based data - Ensure technical compatibility with APIs, and data transformation tools - Test ontology integration in real-world environments
Stakeholders | Individuals or organizations that influence and/or are impacted by the ontology’s development, use, or governance outcomes. They can include project partners, user communities, or organizational managers. | - Provide input on priorities, requirements, and expected impact - Participate in evaluations and feedback processes - Ensure the ontology aligns with the strategic, organizational objectives it supports.
Project leader | The individual responsible for coordinating at managament level the ontology development, application, and governance activities within the project. | - Plan and supervise the activities and outcomes from the ontology lifecycle - Allocate resources, define milestones, and monitor progress - Facilitate communication across technical, organizational, and stakeholder levels

## Lifecycle
Stage | Stage Definition | Activity | Activity definition
1. Ontology requirements specification | Defines the scope and context of the scenario, identifies the actors involved, and clarifies the expected outcomes. During this stage, resources such as use cases or user stories are developed to illustrate the intended applications of the ontology. Both ontological requirements (e.g., key concepts, relations, and constraints to be represented) and non-ontological requirements (e.g., language, licensing, or documentation needs) are collected and formalized through dedicated documentation | 1.1.Knowledge acquisition | Collection of existing knowledge relevant to the domain interest of the ontology. This activity includes identifying domain sources (datasets, reports, expert input) while understanding the concepts, relations and terminology that the ontology will represent. Some of the tasks include in this activity can be: - Reviewing domain literature - Searching for existing ontologies or vocabularies of similar scope - Conducting interviews or workshops with domain experts
|  | 1.2.Requirements elicitation | Identification, documentation, and formalization of the requirements that will guide the ontology development. This activity focuses on capturing both ontological aspects (e.g., main concepts, relations, and constraints to be represented) and non-ontological aspects (e.g., language, licensing, maintenance, or documentation needs). The outcome of this activity is a structured set of requirements that provide a foundation for ontology design and validation, often summarized in dedicated documentation and templates. Some of the tasks included in this activity are: - Developing use cases - Defining the goal and the scope of the ontology - Establishing the ontological and non-ontological requirements through formal documentation and question-driven techniques (competency questions, Ontology Requirements Specification Document (ORSD))
2.Ontology development | Complete process of building the ontology, or extend an existing one, based on the previously defined requirements. It includes conceptualizing the domain knowledge, reusing (non)ontological resources, encoding the ontology using a formal representation language, evaluating its consistency and coverage, and publishing it for access and use by the intended community. | 2.1. Conceptualization | Organizing and structuring the collected knowledge into a conceptual model that represents the domain of interest. This activity includes identifying the main concepts, relationships, and constraints, and grouping them into meaningful hierarchies or modules. The outcome is an simple representation of the ontology’s content, usually expressed through conceptual diagrams, taxonomies, or informal schemas.
|  | 2.2. Reuse | Identification and integration of existing ontological and non-ontological resources that can be reused within the ontology. This activity aims to promote interoperability, consistency, and efficiency by leveraging well-established models instead of creating concepts from scratch. The selection of resources should be guided by their relevance, quality, licensing conditions, and alignment with the ontology’s scope and requirements. Some of the tasks included in this activity are: - Searching for existing resources relevant to the domain - Assessing the suitability and quality of candidate resources - Selecting resources that align with the ontology’s purpose and requirements - Integrating selected elements into the ontology while ensuring conceptual and technical compatibility
|  | 2.3.Enconding | Translation of the conceptual model into a formal representation using an ontology language. This activity involves selecting an appropriate knowledge representation language (e.g., OWL, SKOS, RDFS) and implementing the ontology in that formalism, ensuring that classes, properties, constraints, and metadata are correctly defined. The goal is to produce a machine-readable ontology that preserves the intended meaning of the conceptual model and complies with established modeling and naming conventions. Some of the tasks included in this activity are: - Selecting the ontology language and serialization format based on the ontology’s requirements and intended uses - Encoding classes, properties, axioms, and annotations in the chosen formalism - Applying consistent naming and modeling conventions
|  | 2.4.Evaluation | Verification and validation of the ontology to ensure that it meets the defined requirements and performs as intended. This activity includes checking the ontology’s logical consistency, correctness, completeness, and alignment with the conceptual model and requirements. Evaluation can involve both automated techniques (e.g., reasoning, validation tools) and manual reviews by domain experts. Some of the tasks included in this activity are: - Verifying the logical consistency of the ontology using automated reasoners - Checking the completeness and coverage of the ontology against defined requirements or use cases - Reviewing the ontology content with domain experts to ensure conceptual accuracy - Testing the ontology with example queries or datasets to validate its behavior and usability Verification and validation of the ontology to ensure that it meets the defined requirements and performs as intended. This activity includes checking the ontology’s logical consistency, correctness, completeness, and alignment with the conceptual model and requirements. Evaluation can involve both automated techniques (e.g., reasoning, validation tools) and manual reviews by domain experts. Some of the tasks included in this activity are: - Verifying the logical consistency of the ontology using automated reasoners - Checking the completeness and coverage of the ontology against defined requirements or use cases - Reviewing the ontology content with domain experts to ensure conceptual accuracy - Testing the ontology with example queries or datasets to validate its behavior and usability Activar la compatibilidad con lectores de pantalla Para habilitar la compatibilidad con lectores de pantalla, pulsa ⌘+Opción+Z. Para obtener información acerca de las combinaciones de teclas, pulsa ⌘barra diagonal.
|  | 2.5. Publication | Making the ontology and its related resources available for access and use by the intended community. This activity ensures that the ontology is properly documented, published in accessible formats, and distributed through appropriate platforms or repositories. The goal is to promote visibility, accessibility, and reuse of the ontology by both humans and machines. Some of the tasks included in this activity are: - Selecting suitable platforms or repositories for ontology publication - Preparing and providing accompanying documentation and usage guidelines - Ensuring accessibility and discoverability of the ontology and related resources - Communicating and disseminating the ontology release to the intended users
3. Integration and deployment | Implementation and operational use of the ontology within real systems, applications, or workflows. In this stage, the ontology moves from the development context to an integration and operational use context. The goal is to ensure that the ontology can be effectively deployed, connected to existing data and software components, and validated in real usage contexts. | 3.1. Integration in data space infrastructure | Incorporation of the ontology into the technical or organizational environment for which it was developed. This activity focuses on connecting the ontology with other components such as data sources, knowledge graphs, software systems, or services. But also at organizational level. That is, connect the ontology with the other project components (technical and/or organizational).
|  | 3.2. Deployment | Installation and configuration of the ontology in its target environment. This activity ensures that the ontology is correctly deployed and accessible to users and systems according to the project’s technical requirements. Some of the tasks included in this activity are: - Monitoring system behavior and usage after deployment to ensure stability and accessibility
4. Maintenance | Management of the ontology over time once it has been developed and deployed, ensuring its long-term sustainability. It covers procedures for change management, versioning, collaboration, and communication with users and stakeholders. | 5.1. Bugs management | Detection, reporting, and correction of errors or inconsistencies identified in the ontology after its release. This activity ensures that technical or modeling issues are addressed in a timely manner to maintain the ontology’s reliability and correctness. Some of the tasks included in this activity are: - Documenting fixes and communicating them to users through release notes or changelogs
|  | 5.2. Ontology evolution | Improvement and controlled modification of the ontology to reflect changes in the conceptual model, domain knowledge, or user requirements. This activity focuses on updating the ontology’s structure, semantics, and scope to keep it aligned with its intended purpose and the evolving context. It also involves documenting and managing these changes to ensure transparency and traceability. Some of the tasks included in this activity are: - Identifying and assessing new requirements, domain changes, or conceptual inconsistencies - Updating the ontology’s conceptual model by adding, modifying, or deprecating classes, properties, or relations - Reviewing proposed changes with domain experts and governance bodies - Documenting and publishing updated versions of the ontology with clear change logs
|  | 5.3. Versioning management | Application of procedures for controlling and documenting ontology versions. This activity ensures that every change in the ontology is properly recorded, traceable, and accessible. Versioning management supports reproducibility, citation, and long-term preservation of the ontology. Some of the tasks included in this activity are: - Defining a versioning policy - Assigning and maintaining persistent IRIs for each released version of the ontology - Managing repositories and archives to ensure past versions remain accessible - Documenting changes and maintaining release notes or changelogs for each version - Communicating version updates and their implications to users and collaborators

## RACI
Stage | Activities / Roles | Ontology engineer | Domain expert | System developer | Stakeholder | Project leader | R: Responsible | Recognized as the actual owner of a project or task, the Responsible individual is expected to develop and complete the work assigned to them. | 1...n
Requirements specification | Knowledge acquisition | R | C | - | I | A | A: Accountable | Accountable ensures the work is getting done per guidelines and following the agreed timeline. They sign off on the work and determine whether the deliverable or task is indeed completed and if it meets quality standards. | 1
| Requirements elicitation | R | C | C | - | - | C: Consulted | Consulted parties are typically the people who provide input based on their domain of expertise or how a task will impact their future project work.‍ | 0...n
Development | Conceptualization | R - A | C | - | I | - | I: Informed | Informed stakeholders simply need to be kept in the loop on project progress. They don’t need to be roped into the details of every deliverable. | 0...n
| Ontology reuse | R - A | C | - | - | -
| Encoding | R - A | - | - | - | -
| Evaluation | R - A | C | - | I | -
| Publication | R - A | C | - | I | -
Integration and deployment | Integration | C | - | R | I | A
| Deployment | C | - | R | I | A
Maintenance | Bugs managament | R | - | C | - | A
| Ontology evolution | R | C | - | I | A
| Versioning management | R | C | - | I | A
Dissemination & Adoption | Dissemination | C | - | - | R - A | A
| Adoption monitoring | C | - | C | R - A | A

## Terminology
Term | Definition
Ontology lifecycle | Period of time that describes the evolution of an ontology, from its conception until its retirement (i.e., when the ontology is no longer available to access and use). It represents a simplified view that abstract from the differences between the ways ontologies are developed, deployed and used. It is the temporal dimension of the governance framework.
Ontology lifecycle model | Framework that encompasses the processes, activities and tasks involved in the lifecycle of the ontology, organized by stages, that follow a temporal and structured sequence to support its governance.
Stage | Period of time within the ontology lifecycle model that reflects a specific state of the ontology's realization. They may partially overlap in time, as activities of one stage can inform, influence, or re-trigger actions in another.
Activity | A cohesive group of tasks that take place during a stage. Activities can happen in a sequence or in parallel, and they can occur once during the life cycle or are cycled through repeatedly.
Role | A role is a defined position or function within a governance framework that groups a set of responsibilities, and accountabilities assigned to an individual or organizational unit. In addition, one individual can have more than one role.
Task | A well-defined action within a process, intended to achieve a specific outcome. Related tasks are usually grouped to form activities, and each task is assigned to one or more roles.
RACI Matrix | RACI is a type of Responsibility Assignment Matrix (RAM) which identifies inside of a project who are the participants and to what degree they interact with defined activities. The columns of the matrix identify the roles. The rows indicate the activities. The cells of the matrix specify degrees of authority or responsability types between columns and rows. In the RACI matrix there are four types of interaction: - Responsible: Recognized as the actual owner of a project or task, the Responsible individual is expected to develop and complete the work assigned to them. There must be at least one role asigned as Responsible but there can be multiple roles and individuals asigned as Responsible. - Accountable: Accountable ensures the work is getting done per guidelines and following the agreed timeline. They sign off on the work and determine whether the deliverable or task is indeed completed. There can be only one role assigned to this interaction. - Consulted: Consulted parties are typically the people who provide input based on their domain of expertise or how a task will impact their future project work.‍ There are no restrictions on the number of roles asigned. - Informed: Informed stakeholders simply need to be kept in the loop on project progress. They don’t need to be roped into the details of every deliverable. There are no restrictions on the number of roles asigned.